Yes. Based on the consultancy framework we established, I recommend making the CAIAS consultancy module a single end-to-end website workflow rather than separate manual forms. The portal should capture the consultancy from signed MoU/Consultancy Agreement → registration → execution → progress → payment → closure → final record.

This structure also follows common university consultancy controls: prior institutional routing, written terms, institutional receipt of consultancy payments, monitoring, and closure records. ([SRHU](https://srhu.edu.in/policies-guidelines/policy-for-consultancy-services/?utm_source=chatgpt.com "Policy for Consultancy Services - SRHU"))

# CAIAS Consultancy Portal – Complete Workflow & Field Specification

# 1. Overall Workflow

Department identifies/receives consultancy opportunity

↓

Internal discussion with HOD / concerned faculty

↓

MoU / Consultancy Agreement / Work Order signed

↓

Online Consultancy Registration

↓

System validates submission

↓

Consultancy ID automatically generated

↓

CAIAS Consultancy Record created

↓

Consultancy undertaken

↓

Periodic updates / milestones / documents / payments recorded

↓

Consultancy completed

↓

Online Closure / Exit Form

↓

Final payment and client acceptance verified

↓

Closure Record generated

↓

Consultancy Services Register automatically updated

────────────────────────────────────────────────────────────────────────────────

# 2. Portal User Roles

The portal should have role-based access.

| Role | Main Access |
| --- | --- |
| **Department User / Faculty Consultant** | Create and manage consultancy |
| **HOD** | Verify department details and consultancy |
| **CAIAS Consultancy Administrator** | Monitor, verify, maintain records |
| **Finance / Accounts** | Verify institutional payments |
| **Principal / Competent Authority** | View/approve where required |
| **System Administrator** | Technical administration |
| **Read-only/Audit User** | View records and reports |

## Important

The faculty/department should not create the Consultancy ID manually.

The system generates it automatically after successful submission of the Online Consultancy Registration.

Example:

CAIAS/CON/2026-27/001

────────────────────────────────────────────────────────────────────────────────

# 3. Dashboard – Screen 1

After login, the department/faculty should see:

## My Consultancy Dashboard

Summary Cards

Draft

Submitted

Under Verification

Active

On Hold

Completed

Closed

Rejected

## Buttons

**+ New Consultancy**

My Consultancy Records

Pending Actions

Progress Updates

Closure

Documents

Download Records

## Search / Filter

Consultancy ID

Consultancy Title

Client

Department

Faculty Consultant

Status

Academic Year

Date Range

────────────────────────────────────────────────────────────────────────────────

# 4. Screen 2 – Start New Consultancy

When the user clicks + New Consultancy:

## Preliminary Question

Has an MoU / Consultancy Agreement / Work Order been signed?\*

Dropdown:

Yes – MoU

Yes – Consultancy Agreement

Yes – Work Order / Service Agreement

No

## System Rule

If No, display:

Consultancy registration cannot be submitted until the applicable written agreement/engagement document is available.

The user can save the application as Draft, but cannot submit it.

This is important because university consultancy policies commonly require written terms before execution. ([SRHU](https://srhu.edu.in/policies-guidelines/policy-for-consultancy-services/?utm_source=chatgpt.com "Policy for Consultancy Services - SRHU"))

────────────────────────────────────────────────────────────────────────────────

# 5. Screen 3 – Department Details

Most of these fields should be auto-populated from the CAIAS employee/department database.

## A. Institutional Details

| FieldTypeRequired |  |  |
| --- | --- | --- |
| Academic Year | Auto | Yes |
| Department | Auto/Dropdown | Yes |
| School/Faculty | Auto | Yes |
| HOD Name | Auto | Yes |
| Department Consultancy Coordinator | Dropdown | Yes |
| Faculty Consultant / Principal Consultant | Dropdown | Yes |
| Employee ID | Auto | Yes |
| Official Email | Auto | Yes |
| Contact Number | Auto | Yes |

## System-generated

Registration Date

Registration Time

Created By

Last Updated

Application Status

────────────────────────────────────────────────────────────────────────────────

# 6. Screen 4 – Client / Industry Details

# Client Information

## Client Type\*

Dropdown:

Private Company

Public Sector Undertaking

Government Department

Government Agency

NGO / Non-Profit Organisation

Educational Institution

Research Organisation

Professional Organisation

Startup

Individual / Professional

Other

## Client Details

| FieldRequired |  |
| --- | --- |
| Organisation Name | Yes |
| Registered Address | Yes |
| City | Yes |
| State | Yes |
| Country | Yes |
| PIN/Postal Code | Yes |
| Website | Optional |
| GST Number | Optional |
| PAN / Registration Number | Optional |
| Client Industry/Sector | Yes |

## Authorised Contact

Name\*

Designation\*

Official Email\*

Mobile Number\*

Department/Division

Address

## Optional

Alternate Contact Person

Alternate Email

Alternate Mobile

────────────────────────────────────────────────────────────────────────────────

# 7. Screen 5 – Consultancy Details

# Basic Consultancy Information

## Consultancy Title\*

Short descriptive title.

## Nature of Consultancy\*

Dropdown:

Advisory / Expert Consultation

Training / Capacity Building

Technical Consultancy

Business Consultancy

Management Consultancy

IT / Software Consultancy

Data / Analytics Consultancy

Testing / Analysis

Design / Development

Feasibility Study

Audit / Assessment

Documentation / Report Preparation

Social / Community Consultancy

Research-based Consultancy

Other

## Consultancy Domain\*

Multi-select:

Management

Commerce

Finance

Computer Science / IT

Data Science / AI

Science

Arts / Humanities

Social Sciences

Education

Sustainability

Entrepreneurship

Marketing

HR

Operations

Other

## Consultancy Category

Dropdown:

Expertise Intensive

Infrastructure Intensive

Expertise + Infrastructure

Multidisciplinary

This distinction is useful because university consultancy policies commonly distinguish expertise-driven assignments from assignments requiring institutional infrastructure/resources. ([SRHU](https://srhu.edu.in/policies-guidelines/policy-for-consultancy-services/?utm_source=chatgpt.com "Policy for Consultancy Services - SRHU"))

────────────────────────────────────────────────────────────────────────────────

# 8. Screen 6 – Consultancy Description

## Problem / Requirement of Client\*

Long-text field.

## Objective of Consultancy\*

Long-text field.

## Scope of Work\*

Long-text field.

## Expected Outcomes\*

Long-text field.

## Key Deliverables\*

Repeating field:

+ Add Deliverable

Each deliverable:

Deliverable Name\*

Description

Expected Date

Responsible Consultant

Example:

Requirement Analysis

Training Programme

Prototype

Advisory Report

Final Consultancy Report

────────────────────────────────────────────────────────────────────────────────

# 9. Screen 7 – Agreement Details

## Agreement Type\*

Dropdown:

MoU

Consultancy Agreement

Work Order

Service Agreement

Letter of Engagement

Other

## Agreement Information

| FieldRequired |  |
| --- | --- |
| Agreement Number / Reference | Yes |
| Agreement Date | Yes |
| Start Date | Yes |
| End Date | Yes |
| Renewal / Extension Clause | Optional |
| Confidentiality Clause | Yes/No |
| IP Clause | Yes/No |
| Payment Terms Included | Yes/No |

## Upload

Signed Agreement\*

PDF only.

Recommended:

Maximum file size: 10 MB

PDF preferred

Multiple files allowed if agreement has annexures

## Additional Uploads

Work Order

Client Letter

Scope of Work

Technical Annexure

NDA

Other Supporting Document

Optional unless applicable.

────────────────────────────────────────────────────────────────────────────────

# 10. Screen 8 – Consultancy Team

## Principal Consultant\*

Select CAIAS faculty/staff.

Auto-populate:

Name

Employee ID

Department

Designation

## Add Team Member

Button:

+ Add Consultant

For each:

Name\*

Employee ID

Department\*

Designation

Role in Consultancy\*

Estimated Contribution / Hours

Percentage Contribution — Optional

## Role Dropdown

Principal Consultant

Co-Consultant

Technical Expert

Subject Matter Expert

Project Coordinator

Research Support

Administrative Support

Other

## External Expert

If applicable:

Is an external expert involved?

Yes

No

If Yes:

Name

Organisation

Expertise

Role

Engagement Terms

Supporting Document

────────────────────────────────────────────────────────────────────────────────

# 11. Screen 9 – Timeline

## Consultancy Start Date\*

## Expected Completion Date\*

## Consultancy Duration

Auto-calculated

Example:

82 Days

## Milestones

Repeating section:

| FieldRequired |  |
| --- | --- |
| Milestone | Yes |
| Description | Yes |
| Start Date | Yes |
| Expected Completion | Yes |
| Responsible Person | Yes |
| Status | Auto/Dropdown |

Status:

Not Started

In Progress

Completed

Delayed

On Hold

────────────────────────────────────────────────────────────────────────────────

# 12. Screen 10 – Financial Details

This is an important section.

# Consultancy Fee

## Total Consultancy Value\*

₹ \_\_\_\_\_\_\_\_

## Payment Structure\*

Dropdown:

Full Payment After Completion

Advance + Final Payment

Milestone-based Payment

Monthly Payment

Other

## Payment Schedule

Repeating section:

| FieldRequired |  |
| --- | --- |
| Payment Stage | Yes |
| Amount | Yes |
| Due Date | Yes |
| Payment Status | Auto/Finance |
| Payment Reference | Finance |
| Payment Date | Finance |

## Example

| StageAmountStatus |  |  |
| --- | --- | --- |
| Advance | ₹1,00,000 | Received |
| Milestone 1 | ₹75,000 | Pending |
| Final | ₹75,000 | Pending |

## Important Portal Rule

Payment should be recorded as being made to the designated CAIAS institutional account, not directly to an individual faculty member.

This is consistent with university consultancy frameworks that route consultancy payments through the institution. ([SRHU](https://srhu.edu.in/policies-guidelines/policy-for-consultancy-services/?utm_source=chatgpt.com "Policy for Consultancy Services - SRHU"))

The portal should not display or collect bank-account details from faculty.

Instead:

**Payment instructions:** As provided by CAIAS Finance/Accounts.

────────────────────────────────────────────────────────────────────────────────

# 13. Screen 11 – Institutional Resources

## Will CAIAS resources be used?\*

Yes

No

If No → proceed.

If Yes, display:

## Resources Required

Checkboxes:

Laboratory

Computer Systems

Software

Equipment

Classroom

Auditorium

Meeting Room

Innovation / Incubation Facility

Library / Database

Data / Computing Resources

Other

## Resource Details

Resource

Purpose

Estimated Usage

Department/Facility

Cost, if applicable

This helps distinguish expertise-only consultancy from consultancy involving institutional infrastructure. ([SRHU](https://srhu.edu.in/policies-guidelines/policy-for-consultancy-services/?utm_source=chatgpt.com "Policy for Consultancy Services - SRHU"))

────────────────────────────────────────────────────────────────────────────────

# 14. Screen 12 – Intellectual Property & Confidentiality

## Intellectual Property

Is IP expected to be generated?\*

Yes

No

Not Applicable

If Yes:

Type of IP

Ownership

Commercialisation Rights

Registration Responsibility

Supporting Clause / Agreement Reference

## IP Type

Patent

Copyright

Trademark

Design

Software

Database

Know-how

Technical Documentation

Other

## Confidentiality

Does the consultancy involve confidential information?\*

Yes

No

If Yes:

NDA available?

Yes

No

Upload NDA if applicable.

Written terms should govern confidentiality and IP where relevant. ([SRHU](https://srhu.edu.in/policies-guidelines/policy-for-consultancy-services/?utm_source=chatgpt.com "Policy for Consultancy Services - SRHU"))

────────────────────────────────────────────────────────────────────────────────

# 15. Screen 13 – Documents

Create a dedicated Document Checklist.

## Mandatory

| DocumentRequirement |  |
| --- | --- |
| Signed MoU / Consultancy Agreement / Work Order | **Mandatory** |
| Scope of Work / Terms of Reference | Mandatory if separate |
| Client Request / Engagement Letter | Mandatory if applicable |

## Conditional

| DocumentRequirement |  |
| --- | --- |
| NDA | If confidentiality applies |
| Technical Proposal | If applicable |
| Financial Proposal | If applicable |
| IP Agreement | If IP is involved |
| Resource Approval | If institutional resources require separate approval |
| Other Supporting Document | Optional |

## Upload Rules

PDF preferred

Maximum file size: 10 MB per file

Multiple files permitted

File name automatically sanitised

Upload date/time recorded

Uploaded by recorded

Version number maintained

────────────────────────────────────────────────────────────────────────────────

# 16. Screen 14 – Declaration

Before submission:

## Department Declaration

Checkbox:

☐ I confirm that the information provided in this registration is accurate and complete.

☐ I confirm that the consultancy is being undertaken through CAIAS and in accordance with applicable institutional policies and guidelines.

☐ I confirm that the consultancy agreement / applicable written engagement has been executed.

☐ I confirm that all consultancy payments shall be routed through the designated CAIAS institutional account.

☐ I confirm that CAIAS resources shall be used only as declared and authorised.

## Declaration By

Auto-populated:

Faculty Consultant

Employee ID

Department

Date

────────────────────────────────────────────────────────────────────────────────

# 17. Screen 15 – Review Before Submission

This should be a read-only summary.

Sections:

Department Details

Client Details

Consultancy Details

Agreement

Consultancy Team

Timeline

Financial Details

Resources

IP & Confidentiality

Documents

Declaration

Buttons:

Edit

Save Draft

Submit Consultancy Registration

────────────────────────────────────────────────────────────────────────────────

# 18. Submission Confirmation

After submission:

**Consultancy Registration Submitted Successfully**

Display:

## Consultancy ID

CAIAS/CON/2026-27/001

## Registration Date

08 September 2026

## Status

Submitted

## Next Step

The consultancy registration is now available in the CAIAS Consultancy Portal for verification/record.

The user can:

Download Registration Record

View Consultancy

Return to Dashboard

────────────────────────────────────────────────────────────────────────────────

# 19. Automatic Consultancy ID

The system should generate:

CAIAS/CON/YYYY-YY/XXX

Example:

CAIAS/CON/2026-27/001

## Rules

`CAIAS` = Institution

`CON` = Consultancy

`2026-27` = Academic Year

`001` = sequential number

The number should never be reused, even if a consultancy is cancelled later.

────────────────────────────────────────────────────────────────────────────────

# 20. Screen 16 – Consultancy Record

Once registered, the portal becomes the main consultancy record.

Header:

**CAIAS/CON/2026-27/001**

Status: ACTIVE

## Tabs

Overview

Consultancy Details

Team

Agreement

Milestones

Progress

Payments

Documents

Client Feedback

Closure

Audit Trail

────────────────────────────────────────────────────────────────────────────────

# 21. Screen 17 – Progress Update

The consultant should periodically update the consultancy.

## Update Information

Update Date\*

Reporting Period\*

Current Status\*

Work Completed\*

Work in Progress\*

Pending Activities

Challenges / Issues

Corrective Action

Next Planned Activity

Overall Progress %

## Status

On Track

Delayed

On Hold

Completed

## Upload

Progress Report

Meeting Minutes

Deliverable

Client Communication

Other Supporting Document

────────────────────────────────────────────────────────────────────────────────

# 22. Screen 18 – Milestone Update

For each milestone:

## Display

Milestone 1 – Requirement Analysis

Planned Date

Actual Start

Actual Completion

Responsible Consultant

Status

Remarks

## Status

Not Started

In Progress

Completed

Delayed

Cancelled

## Upload

Supporting evidence/document.

────────────────────────────────────────────────────────────────────────────────

# 23. Screen 19 – Payment Tracking

This should be visible to the consultant but financial verification should be controlled by Finance.

## Consultant View

Total Consultancy Value

Amount Received

Amount Pending

Payment Stage

Payment Status

## Finance View

Amount Received

Date

CAIAS Account Reference

Receipt / Transaction Reference

TDS / Applicable statutory deduction, if applicable

Remarks

## Status

Pending

Partially Received

Received

Overdue

Waived/Adjusted — only if institutionally authorised

────────────────────────────────────────────────────────────────────────────────

# 24. Screen 20 – Document Repository

Every consultancy should have a central document folder.

## Categories

Agreement

MoU

Consultancy Agreement

Work Order

NDA

Execution

Progress Reports

Meeting Records

Deliverables

Technical Documents

Financial

Payment Records

Invoices

Receipts

Closure

Final Report

Client Acceptance

Feedback

Closure Form

## System Features

Upload

Download

View

Version

Replace/New Version

Date

Uploaded By

────────────────────────────────────────────────────────────────────────────────

# 25. Screen 21 – Consultancy Closure / Exit Form

This becomes available only when the consultant selects:

Request Closure

## Completion Details

Actual Completion Date\*

Total Duration — Auto

Consultancy Status\*

Final Progress %

## Work Completion

Were all agreed deliverables completed?\*

Yes

Partially

No

If Partially:

Reason / Explanation\*

## Deliverables

Each deliverable:

Planned

Completed

Completion Date

Evidence Document

Remarks

────────────────────────────────────────────────────────────────────────────────

# 26. Screen 22 – Client Acceptance

## Client Acceptance\*

Yes

No

Not Required

If Yes:

Client Acceptance Date

Client Representative

Acceptance Document

## Client Feedback

Overall Satisfaction

Comments

Suggestions

## Rating

Optional 1–5 scale:

1 — Poor

2 — Fair

3 — Good

4 — Very Good

5 — Excellent

────────────────────────────────────────────────────────────────────────────────

# 27. Screen 23 – Final Financial Closure

## Payment Status

Is the full consultancy amount received?\*

Yes

No

If No:

Amount Pending

Reason

Expected Payment Date

## Finance Confirmation

Total Agreement Value

Total Received

Balance

Finance Verification

Finance Remarks

## Important

The system should not allow final closure as "Completed & Closed" until Finance confirms the required financial status, unless an authorised exception is recorded.

────────────────────────────────────────────────────────────────────────────────

# 28. Screen 24 – Final Consultancy Report

## Upload

Final Consultancy Report\*

PDF.

Optional:

Final Technical Report

Deliverables

Client Acceptance

Photographs

Presentation

Output/Outcome Evidence

## Final Outcome

Consultancy completed successfully

Consultancy partially completed

Consultancy terminated

Consultancy cancelled

If terminated/cancelled:

Reason mandatory.

────────────────────────────────────────────────────────────────────────────────

# 29. Screen 25 – Final Declaration

## Consultant Declaration

☐ I confirm that the consultancy activities recorded in this portal have been completed as stated.

☐ All agreed deliverables have been submitted or their status has been recorded.

☐ All relevant consultancy documents have been uploaded.

☐ Financial details have been accurately reported.

☐ The information provided is true and complete.

## Submit Closure

Submit Consultancy Closure

────────────────────────────────────────────────────────────────────────────────

# 30. Screen 26 – Final Closure Verification

The CAIAS Consultancy Administrator reviews:

Registration

Agreement

Progress

Deliverables

Payment

Final Report

Client Acceptance

Documents

## Verification Result

Closure Verified

Clarification Required

Returned for Correction

────────────────────────────────────────────────────────────────────────────────

# 31. Final Closure Record

After verification:

## Status

COMPLETED & CLOSED

System generates:

CAIAS/CON/2026-27/001 – Closure Record

The record contains:

Consultancy ID

Department

Consultant(s)

Client

Consultancy Title

Agreement Reference

Start Date

Completion Date

Consultancy Value

Payment Status

Deliverables

Outcome

Client Acceptance

Final Report

Closure Date

────────────────────────────────────────────────────────────────────────────────

# 32. Status Logic

I recommend keeping the status system simple.

| StatusMeaning |  |
| --- | --- |
| **Draft** | Application being prepared |
| **Submitted** | Registration submitted |
| **Under Verification** | Being checked |
| **Clarification Required** | Information/document required |
| **Registered** | Consultancy officially registered |
| **Active** | Consultancy underway |
| **On Hold** | Temporarily suspended |
| **Delayed** | Completion date exceeded |
| **Closure Requested** | Consultant submitted closure |
| **Closure Under Verification** | Final record being checked |
| **Completed & Closed** | Consultancy formally closed |
| **Cancelled** | Consultancy cancelled |
| **Rejected** | Registration not accepted |

## Recommended workflow

Draft → Submitted → Under Verification → Registered → Active → Closure Requested → Closure Under Verification → Completed & Closed

────────────────────────────────────────────────────────────────────────────────

# 33. Clarification Workflow

If information is missing:

Under Verification

↓

Clarification Required

↓

Department receives notification

↓

Department edits required fields

↓

Resubmit

↓

Under Verification

The system should retain the previous version in the audit trail.

────────────────────────────────────────────────────────────────────────────────

# 34. Automatic Notifications

The portal should generate notifications for:

## Department

Registration submitted

Clarification required

Registration verified

Consultancy approaching completion

Milestone overdue

Closure due

Closure accepted

## HOD

New consultancy submitted

Clarification required

Consultancy active

Closure submitted

## Finance

New consultancy registered

Payment expected

Payment update required

Final financial closure

## Administrator

New registration

Pending verification

Delayed consultancy

Closure request

Overdue payment

Missing documents

────────────────────────────────────────────────────────────────────────────────

# 35. Automatic Alerts

The system should automatically flag:

## 30 Days Before Completion

Consultancy approaching scheduled completion.

## Completion Date Reached

Consultancy completion date reached. Please update status.

## Completion Date Passed

Status automatically changes to:

Delayed

unless an extension has been recorded.

## Missing Payment

Financial closure pending.

## Missing Closure

Consultancy completed according to timeline but closure has not been submitted.

────────────────────────────────────────────────────────────────────────────────

# 36. Extension Workflow

Do not edit the original completion date directly.

Instead:

## Request Extension

Fields:

Existing Completion Date

Proposed New Completion Date\*

Reason\*

Revised Timeline

Client Consent — if applicable

Supporting Document

## Status

Extension Requested → Verified → Revised Completion Date

The original date remains in the audit trail.

────────────────────────────────────────────────────────────────────────────────

# 37. Audit Trail

Every important action should be recorded.

| Date/TimeUserActionPreviousNew |  |  |  |  |
| --- | --- | --- | --- | --- |
| 08-09-26 | Faculty | Submitted | Draft | Submitted |
| 09-09-26 | Admin | Verified | Submitted | Registered |
| 10-09-26 | Faculty | Started | Registered | Active |
| 15-10-26 | Faculty | Update | Active | Active |
| 30-11-26 | Faculty | Closure | Active | Closure Requested |

This is particularly important for institutional records and accreditation/audit purposes.

────────────────────────────────────────────────────────────────────────────────

# 38. Auto-Generated Documents

The portal should generate three official PDFs.

## PDF 1 – Consultancy Registration Record

Generated after registration.

Contains:

Consultancy ID

Department

Client

Consultancy details

Agreement details

Team

Timeline

Financial summary

Resources

IP/confidentiality

Document checklist

Declaration

## PDF 2 – Consultancy Progress Record

Generated whenever required.

Contains:

Consultancy ID

Current status

Milestones

Progress

Payments

Key updates

Documents available in portal

## PDF 3 – Consultancy Closure Record

Generated after closure.

Contains:

Registration details

Final consultancy details

Deliverables

Client acceptance

Financial closure

Final outcome

Closure declaration

Closure date

Uploaded documents should not be embedded into these PDFs.

Instead:

**Supporting Document: Available in CAIAS Consultancy Portal**

with the document/reference number.

────────────────────────────────────────────────────────────────────────────────

# 39. Consultancy Register – Automatic Entry

The portal should automatically populate the CAIAS Consultancy Services Register.

Suggested fields:

Register Field

Consultancy ID

Academic Year

Department

Consultant

Client

Consultancy Title

Consultancy Type

Start Date

Completion Date

Consultancy Value

Amount Received

Status

Agreement Reference

IP Involved

CAIAS Resources Used

Closure Date

Client Feedback

Final Report

Remarks

The department should not separately maintain this register manually if the portal is functioning correctly.

────────────────────────────────────────────────────────────────────────────────

# 40. Mandatory vs Optional – Final Rule

A simple colour/status system can help the developer.

## 🔴 Mandatory

Must be completed before submission.

## 🟡 Conditional Mandatory

Required only when the relevant option is selected.

Example:

**IP Generated? → Yes**

Then IP details become mandatory.

## ⚪ Optional

Can be left blank.

## 🔵 Auto-generated

System creates the value.

Examples:

Consultancy ID

Registration Date

Submission Date

Status

Created By

Last Updated

Duration

Closure Date

────────────────────────────────────────────────────────────────────────────────

# 41. Recommended Mandatory Upload Checklist

For initial registration:

**Signed MoU / Consultancy Agreement / Work Order – Mandatory**

Scope of Work / Terms of Reference – Mandatory if separate

Client Request / Engagement Letter – Conditional

NDA – Conditional

IP Agreement – Conditional

Other supporting documents – Optional

For closure:

Final Consultancy Report – Mandatory

Deliverable Evidence – Conditional

Client Acceptance – Conditional/required where applicable

Final Payment/Finance Record – System/Finance

Client Feedback – Recommended

────────────────────────────────────────────────────────────────────────────────

# 42. What the Department Actually Does

To keep the system simple for faculty, their actual work should be only:

## Before Consultancy

1. Discuss with industry/client

↓

2. Finalise terms

↓

3. Sign MoU / Consultancy Agreement / Work Order

↓

## Portal

4. Login

↓

5. Fill Online Consultancy Registration

↓

6. Upload agreement

↓

7. Submit

↓

8. Receive Consultancy ID

↓

## During Consultancy

9. Undertake consultancy

↓

10. Update milestones/progress

↓

11. Upload relevant records

↓

## After Consultancy

12. Submit Closure / Exit Form

↓

13. Upload final report

↓

14. Complete client acceptance/feedback

↓

15. Final closure

That is the workflow I would recommend for CAIAS.

────────────────────────────────────────────────────────────────────────────────

# 43. Final Portal Menu Structure

For the website developer, the complete module can be represented as:

CAIAS Website → Consultancy Services

## Department Dashboard

Dashboard

New Consultancy

My Consultancies

Active Consultancies

Progress Updates

Documents

Payments

Closure

Reports

## Administrator Dashboard

All Consultancies

Pending Verification

Active Consultancies

Delayed Consultancies

Closure Requests

Finance Pending

Reports

Consultancy Register

Audit Trail

## Individual Consultancy

Overview | Details | Agreement | Team | Milestones | Progress | Payments | Documents | Client Feedback | Closure | Audit Trail

────────────────────────────────────────────────────────────────────────────────

# Final recommended architecture

I would not create separate Google Forms, manual registers, or separate Word forms for this process.

The website should have one master Consultancy Record, with different screens appearing at different stages:

Registration Screen → Active Consultancy Record → Progress Updates → Closure Screen → Final Closure Record

The underlying database record should remain the same throughout the lifecycle. This avoids duplicate data entry and gives CAIAS one auditable institutional record for every consultancy.

This approach is also consistent with the broader university practice of routing consultancy through institutional channels, documenting the engagement, monitoring execution, and maintaining institutional financial records. ([SRHU](https://srhu.edu.in/policies-guidelines/policy-for-consultancy-services/?utm_source=chatgpt.com "Policy for Consultancy Services - SRHU"))

If implemented this way, the consultancy ID becomes the single reference number for the entire engagement—from the first registration through final closure.

────────────────────────────────────────────────────────────────────────────────

# 44. Developer-Ready Business Rules & Control Specification

The workflow above defines the functional screens and lifecycle. The following rules make the specification sufficiently precise for development and testing.

# 44.1 Approval and Verification Workflow

The portal shall distinguish between verification and approval.

## Registration workflow

Draft

↓

Submitted

↓

HOD Verification

(if HOD verification is configured as mandatory for the department)

↓

CAIAS Verification

↓

Competent Authority Approval

(only when required by CAIAS policy/delegation rules)

↓

Registered

↓

Active

## Rules

Submission creates the Consultancy ID and locks the submitted version from ordinary editing.

The system routes the record to the next configured verifier.

A verifier may:

Verify/forward

Return for clarification

Reject, where rejection authority is permitted

A record returned for clarification becomes **Clarification Required** and may be edited only by the designated department/faculty users.

Resubmission creates a new version while retaining the previous version in the audit trail.

A rejected consultancy remains searchable and auditable but cannot proceed to Active unless a new registration is created or an authorised reopening process is implemented.

Competent Authority approval shall be configurable rather than hard-coded. The system must support a policy/configuration table identifying when approval is required.

The approval decision must record:

Approver

Date/time

Decision

Comments

Approval reference, where applicable

## Important

The system must never silently skip a configured approval stage.

────────────────────────────────────────────────────────────────────────────────

# 45. Status and Workflow-State Model

To keep the user-facing status simple while allowing precise routing, the system should maintain both:

## User-facing Status

Draft

Submitted

Under Verification

Clarification Required

Registered

Active

On Hold

Delayed

Closure Requested

Closure Under Verification

Completed & Closed

Cancelled

Rejected

## Internal Workflow Stage

Draft

Submitted

HOD Verification Pending

CAIAS Verification Pending

Competent Authority Approval Pending

Registered

Active

Extension Pending

Closure Verification Pending

Finance Closure Pending

Completed & Closed

Cancelled

Rejected

The internal workflow stage is for routing and permissions; the user-facing status is for dashboards and reports.

────────────────────────────────────────────────────────────────────────────────

# 46. Role & Permission Matrix

The developer should implement permissions by role and action.

| Action | Faculty/Department | HOD | CAIAS Admin | Finance | Competent Authority | Audit |
| --- | --- | --- | --- | --- | --- | --- |
| Create Draft | Yes | No | Yes, if needed | No | No | No |
| Edit Draft | Yes | No | Yes, if authorised | No | No | No |
| Submit | Yes | No | Yes, if authorised | No | No | No |
| Verify Department | No | Yes | Yes | No | No | No |
| CAIAS Verify | No | No | Yes | No | No | No |
| Approve | No | No | Only if delegated | No | Yes, if required | No |
| Update Progress | Yes | View | View/Edit if authorised | No | View | View |
| Update Payment | No | View | View | Yes | View | View |
| Upload Documents | Yes | Yes, where permitted | Yes | Finance documents only | Yes, where permitted | No |
| Request Closure | Yes | No | Yes, if authorised | No | No | No |
| Verify Closure | No | No | Yes | Financial verification only | Approval if configured | View |
| View Audit Trail | Own records | Department scope | All | Financial scope | Approved scope | All read-only |
| Delete Record | No | No | No | No | No | No |

## Record deletion

Consultancy records must not be physically deleted after submission. Records should be retained according to CAIAS's institutional retention policy. Drafts may be archived rather than deleted.

────────────────────────────────────────────────────────────────────────────────

# 47. Validation Rules

The portal shall perform both client-side and server-side validation.

# 47.1 Date Validation

Agreement Date cannot be later than the date of submission if the agreement is already executed.

Start Date cannot be earlier than Agreement Date unless an authorised exception is recorded.

End Date cannot be earlier than Start Date.

Expected Completion Date cannot be earlier than Consultancy Start Date.

Milestone completion cannot precede milestone start.

Extension New Completion Date must be later than the existing completion date.

# 47.2 Financial Validation

Consultancy Value must be greater than zero unless an authorised zero-value consultancy category is configured.

Payment schedule total should equal the consultancy value, unless an authorised adjustment/rounding rule applies.

Finance-recorded received amounts cannot exceed the agreement value without an authorised adjustment.

Amount Pending = Total Value − Total Received − Authorised Adjustments.

Finance fields must be read-only to faculty.

TDS/statutory deductions must be separately recorded where applicable and must not silently change the contractual consultancy value.

# 47.3 Team Validation

Principal Consultant is mandatory.

Each internal consultant must be identifiable through the institutional employee directory where applicable.

Contribution percentages, if entered, should total 100%.

External experts require supporting engagement information where the external-expert option is selected.

# 47.4 Conditional Validation

The system must dynamically enforce conditional mandatory fields.

Examples:

IP Generated = Yes

→ IP details mandatory.

Confidential Information = Yes

→ NDA/justification fields mandatory according to policy.

CAIAS Resources Used = Yes

→ Resource details mandatory.

Deliverables Completed = Partially

→ Reason mandatory.

Full Payment Received = No

→ Pending amount/reason required.

Termination/Cancelled

→ Reason mandatory.

────────────────────────────────────────────────────────────────────────────────

# 48. Agreement and Document Controls

# 48.1 Agreement Requirement

The applicable signed agreement/engagement document is mandatory before final registration submission.

The system may allow a Draft without the document, but must prevent submission while the mandatory agreement requirement remains unmet.

# 48.2 Document Versioning

Each uploaded document shall maintain:

Document Category

Original File Name

System File Name

Version Number

Uploaded By

Upload Date/Time

Document Status

Replacement/Revision Reference

Replacing a document must create a new version rather than overwrite the historical file.

# 48.3 File Controls

Recommended baseline:

PDF preferred for official records.

Maximum file size: 10 MB per file, configurable.

Multiple files allowed where an agreement contains annexures.

File names sanitised by the system.

Virus/malware scanning should be performed before a file becomes available to other users.

Access to confidential documents must follow role-based permissions.

────────────────────────────────────────────────────────────────────────────────

# 49. Consultancy ID Rules

The Consultancy ID shall follow:

CAIAS/CON/YYYY-YY/XXX

Example:

CAIAS/CON/2026-27/001

## Rules

The sequence is generated by the server/database, not by the browser.

The sequence must be transaction-safe so that two simultaneous submissions cannot receive the same number.

Once issued, the number must never be reused.

Cancellation or rejection does not release the number.

The academic-year sequence may reset at the beginning of each academic year.

The exact academic-year definition shall be configurable according to CAIAS requirements.

The ID must remain the primary reference throughout registration, progress, finance, closure, reports, and audit.

────────────────────────────────────────────────────────────────────────────────

# 50. Approval Configuration

Because approval requirements may change, they should be configurable rather than hard-coded.

The CAIAS administrator should be able to configure:

Whether HOD verification is required.

Whether competent-authority approval is required.

Which consultancy categories require approval.

Whether approval depends on consultancy value.

Whether institutional resources trigger an additional approval.

Whether IP/confidentiality conditions trigger an additional review.

Which role can approve each configured stage.

The configuration itself must be audited.

────────────────────────────────────────────────────────────────────────────────

# 51. Rejection and Return Rules

# 51.1 Return for Clarification

A verifier selects:

Return for Clarification

and must enter:

Reason

Fields/documents requiring correction

Reviewer

Date/time

The faculty receives a notification and may edit only the permitted fields.

# 51.2 Rejection

Where the user has rejection authority:

Rejection reason is mandatory.

Rejected records remain in the system.

The Consultancy ID is not reused.

The rejection event is permanently recorded in the audit trail.

The department is notified.

# 51.3 Reopening

A rejected or closed record must not be silently reopened.

If CAIAS permits reopening, the system must provide an explicit Reopen action with:

Authorising user

Reason

Date/time

Previous status

New status

Supporting document, if required

────────────────────────────────────────────────────────────────────────────────

# 52. Active Consultancy Rules

A consultancy can move to Active only after all configured registration verification/approval stages are complete.

The system should check:

Required agreement present

Required registration fields complete

Required approvals complete

Required conditional documents present

No unresolved clarification

Consultancy not rejected/cancelled

If all conditions are met:

Registered → Active

The system should record the activation date/time and activating user/system event.

────────────────────────────────────────────────────────────────────────────────

# 53. Progress Monitoring Rules

Progress updates should be controlled by the consultancy's reporting requirements.

The system should support:

Monthly updates

Milestone-based updates

Quarterly updates

Custom reporting frequency

The reporting frequency should be configurable per consultancy.

## Automated monitoring

The system should calculate:

Days elapsed

Days remaining

Progress percentage

Overdue milestones

Overdue completion date

Pending closure

Progress percentage should not automatically be treated as a financial or contractual completion measure.

────────────────────────────────────────────────────────────────────────────────

# 54. Extension Workflow

The original completion date must remain unchanged.

## Extension workflow

Active / Delayed

↓

Extension Requested

↓

Review

↓

Approved / Rejected

## Extension record

Each extension must retain:

Original completion date

Proposed completion date

Reason

Revised timeline

Client consent, where applicable

Supporting document

Requested by

Requested date

Approved/rejected by

Decision date

Decision remarks

If approved, the revised date becomes the current completion date while the original date remains visible in history.

────────────────────────────────────────────────────────────────────────────────

# 55. On-Hold Workflow

A consultancy may be placed On Hold only through an explicit action.

Required fields:

Hold reason

Hold start date

Expected resume date, if known

Supporting document, if applicable

Authorised by

The system must record:

Active → On Hold

and later:

On Hold → Active

or

On Hold → Cancelled

The system should not automatically mark a consultancy as Delayed merely because it was On Hold during an authorised period.

────────────────────────────────────────────────────────────────────────────────

# 56. Cancellation and Termination Workflow

Cancellation and termination should be distinct from ordinary closure.

# Cancellation

Use when the consultancy will not proceed or is discontinued before meaningful execution.

Required:

Cancellation reason

Cancellation date

Initiated by

Approval, where required

Financial status

Outstanding obligations

Supporting document

# Termination

Use when an active consultancy is ended before all agreed deliverables are completed.

Required:

Termination reason

Actual termination date

Completed deliverables

Outstanding deliverables

Financial status

Client communication/acceptance, where applicable

Approval, where required

Neither event should erase the consultancy record.

────────────────────────────────────────────────────────────────────────────────

# 57. Closure Gate

The system shall not permit Completed & Closed unless all configured closure gates are satisfied.

## Closure gate checklist

Final completion details entered.

Deliverable status recorded.

Final report uploaded.

Required evidence uploaded.

Client acceptance recorded where applicable.

Client feedback recorded where required/recommended.

Finance has verified the financial status.

Any approved exception is documented.

CAIAS closure verification completed.

Final closure declaration completed.

## Financial exception

If full payment has not been received, closure may proceed only if CAIAS policy permits it and an authorised exception is recorded.

The exception must include:

Reason

Amount outstanding

Expected recovery/action

Authorising officer

Date

Remarks

────────────────────────────────────────────────────────────────────────────────

# 58. Client Acceptance Rules

Client acceptance shall be configurable as:

Mandatory

Conditional

Not Required

The system must not force a client acceptance document when CAIAS policy marks the consultancy as not requiring one.

Where acceptance is required, the closure gate must prevent final closure until the required acceptance information/document is present.

────────────────────────────────────────────────────────────────────────────────

# 59. Finance Controls

Finance shall have a dedicated financial view.

## Finance may record

Invoice/reference number

Payment stage

Amount billed

Amount received

Payment date

Institutional account reference

Receipt/transaction reference

TDS/statutory deduction

Adjustment

Remarks

Verification status

## Faculty may view

Agreement value

Payment stages

Amount received

Amount pending

Payment status

Faculty must not be able to modify Finance verification fields.

The portal must not collect faculty personal bank-account details for consultancy payment routing.

────────────────────────────────────────────────────────────────────────────────

# 60. Notification Rules

Notifications should be generated through configurable channels.

## Minimum recommended channels

Portal notification

Official email

SMS may be added later if CAIAS requires it.

## Notification events

Faculty/Department

Draft submitted

Clarification required

Registration verified

Approval completed

Consultancy registered

Consultancy activated

Milestone approaching

Milestone overdue

Completion approaching

Completion date reached

Consultancy delayed

Extension decision

Closure submitted

Closure returned

Closure completed

Payment received/updated

HOD

Registration requiring verification

Clarification

Consultancy activated

Closure requiring attention

CAIAS Admin

New submission

Pending verification

Delayed consultancy

Extension request

Closure request

Finance pending

Missing documents

Finance

New registered consultancy

Payment stage due

Payment recorded

Financial closure pending

────────────────────────────────────────────────────────────────────────────────

# 61. Reporting & Analytics

The administrator dashboard should provide at least:

# Operational Reports

Consultancies by status

Consultancies by department

Consultancies by academic year

Consultancies by faculty

Consultancies by client type

Consultancies by consultancy category

Active consultancies

Delayed consultancies

On-hold consultancies

Pending closure

Rejected/cancelled consultancies

# Financial Reports

Total consultancy value

Amount received

Amount pending

Payments overdue

Consultancy value by department

Consultancy value by academic year

TDS/statutory deductions, where applicable

# Outcome Reports

Completed consultancies

Client satisfaction ratings

Consultancy outcomes

IP-generated consultancies

Resource-intensive consultancies

Multidisciplinary consultancies

All reports must use the master consultancy record as the source rather than requiring separate manual registers.

────────────────────────────────────────────────────────────────────────────────

# 62. Search, Filters & Export

The administrator should be able to search/filter by:

Consultancy ID

Academic Year

Department

School/Faculty

Consultant

Client

Client type

Consultancy category

Status

Start date

Completion date

Agreement reference

Payment status

IP involvement

Resource usage

Exports should support at least:

Excel/CSV for structured reporting

PDF for official summary reports

Export permissions must follow role-based access.

────────────────────────────────────────────────────────────────────────────────

# 63. Audit Trail Requirements

The audit trail shall be immutable to ordinary users.

For every material event, record:

Date/time

User ID

User role

Action

Record ID

Field changed, where applicable

Previous value

New value

IP/device/session information where institutionally permitted

Reason/comment where required

Examples:

Created

Submitted

Returned

Resubmitted

Verified

Approved

Rejected

Activated

Progress updated

Payment updated

Document uploaded

Document replaced

Extension requested

Extension approved

Put on hold

Resumed

Closure requested

Closure returned

Closure verified

Closed

Cancelled

Terminated

────────────────────────────────────────────────────────────────────────────────

# 64. Security & Access Controls

The developer shall implement:

Role-based access control

Server-side permission checks

Secure authentication

Session timeout

Protection against unauthorised record access

Secure document storage

Audit logging

Input validation

File-type validation

Malware scanning for uploaded files

Backup and recovery procedures

Appropriate encryption for data in transit and at rest, according to institutional IT standards

Sensitive client, financial, agreement, IP, and confidential documents should not be exposed to users who do not have permission to view them.

────────────────────────────────────────────────────────────────────────────────

# 65. Data Model – Recommended Core Entities

The application should be designed around a master consultancy record with related entities.

## Core entities

**Consultancy**

**Consultancy Team Member**

**Client**

**Agreement**

**Deliverable**

**Milestone**

**Progress Update**

**Payment Schedule**

**Payment Transaction**

**Document**

**Client Acceptance**

**Client Feedback**

**Closure**

**Approval**

**Extension**

**Audit Event**

**Notification**

**Master Data / Configuration**

## Principle

The Consultancy entity remains the parent/master record. Related records reference the same Consultancy ID.

────────────────────────────────────────────────────────────────────────────────

# 66. Master Data & Configuration

The following should be configurable by authorised administrators rather than hard-coded:

Academic years

Departments

Schools/Faculties

Consultancy types

Consultancy domains

Consultancy categories

Client types

Team roles

Milestone statuses

Payment statuses

Approval requirements

Reporting frequency

Notification templates

File-size limits

Allowed file types

Closure requirements

Financial exception rules

Changes to configuration must themselves be audited.

────────────────────────────────────────────────────────────────────────────────

# 67. Dashboard KPIs

# Faculty Dashboard

Draft

Submitted

Active

Delayed

Closure Due

Closed

Pending Actions

# CAIAS Admin Dashboard

Total Consultancies

Pending Verification

Approval Pending

Active

Delayed

Closure Pending

Finance Pending

Total Consultancy Value

Amount Received

Amount Pending

The dashboard should provide drill-down from KPI → filtered consultancy list → individual Consultancy Record.

────────────────────────────────────────────────────────────────────────────────

# 68. Record Retention and Archiving

The portal should support institutional retention requirements.

A closed consultancy should move to an Archived logical state or archival repository when the retention policy requires it.

Archiving must not:

Change the Consultancy ID

Remove the audit trail

Delete required financial records

Break document references

Prevent authorised audit access

The retention period itself should be configurable according to CAIAS/institutional policy.

────────────────────────────────────────────────────────────────────────────────

# 69. Accessibility & Usability

The portal should:

Work on desktop and mobile/tablet browsers.

Use clear mandatory/conditional indicators.

Provide meaningful validation messages.

Preserve entered data when validation fails.

Provide Save Draft throughout long forms.

Show a progress indicator for multi-screen registration.

Prevent accidental duplicate submissions.

Provide confirmation before irreversible actions.

Use accessible labels and keyboard-friendly controls.

Clearly distinguish read-only fields from editable fields.

────────────────────────────────────────────────────────────────────────────────

# 70. Developer Acceptance Criteria

The module should be considered ready for production only when the following scenarios pass testing.

## Registration

User can create a draft.

User cannot submit without required agreement/document.

Consultancy ID is generated uniquely.

Required conditional fields are enforced.

Submission creates an audit event.

Correct verification/approval route is triggered.

## Verification

HOD can verify/return/reject according to permission.

CAIAS Admin can verify/return/reject according to permission.

Competent Authority approval is triggered only when configured.

Clarification requests are visible to the originating department.

Previous versions remain auditable.

## Execution

Registered consultancy can become Active only after required gates.

Progress updates can be added.

Milestones can be updated.

Overdue milestones are flagged.

Completion-date alerts operate correctly.

Extensions preserve the original date.

## Finance

Faculty cannot edit Finance records.

Finance can record transactions.

Payment totals reconcile.

Financial status is visible correctly.

Financial closure is required before final closure unless an authorised exception exists.

## Closure

Closure cannot be submitted without required closure fields.

Final report requirement is enforced.

Client acceptance is enforced only when configured.

Closure verification is recorded.

Final Closure Record is generated.

Consultancy Register is updated automatically.

## Audit

Every material status change is logged.

Document versions are retained.

No submitted/closed record can be silently deleted.

Reports reflect the master Consultancy Record.

────────────────────────────────────────────────────────────────────────────────

# 71. Final Recommended End-to-End Architecture

The final CAIAS consultancy architecture should be:

CAIAS Website

↓

Consultancy Services

↓

Department Dashboard

↓

New Consultancy

↓

Draft

↓

Submission

↓

HOD Verification (if configured)

↓

CAIAS Verification

↓

Competent Authority Approval (if configured)

↓

Registered

↓

Active Consultancy Record

↓

Milestones + Progress + Documents + Payments

↓

Extension / On Hold / Delay controls where applicable

↓

Closure Request

↓

Closure Verification

↓

Finance Closure / Authorised Financial Exception

↓

Completed & Closed

↓

Closure Record

↓

Automatic Consultancy Services Register

↓

Reports + Audit + Archive

────────────────────────────────────────────────────────────────────────────────

# 72. Final Implementation Principle

The CAIAS Consultancy Portal should be implemented as one auditable master record per consultancy, not as a collection of disconnected forms.

The Consultancy ID must remain the single reference throughout the entire lifecycle.

The portal should enforce:

one record → one ID → one controlled workflow → one document repository → one audit trail → one final closure record → one institutional register entry.

The faculty/department should enter information only once wherever possible. Subsequent screens should reuse existing data rather than asking users to re-enter department, client, consultant, agreement, financial, or timeline information.

The system should automate status transitions, reminders, register updates, document versioning, and reporting while keeping institutional verification, approval, financial verification, and audit controls under role-based access.

This produces a cleaner, more maintainable and more auditable CAIAS consultancy process than separate Google Forms, spreadsheets, Word forms, and manually maintained registers.