CHRIST ACADEMY INSTITUTE FOR ADVANCED STUDIES

Light to Enlighten

CONSULTANCY SERVICES
UPDATED SYSTEM RECORD & WORKFLOW

Review outcome: The original 3-page mock-up has been reorganized so that information available at registration is separated from information generated during monitoring and closure. This avoids presenting future dates, progress, payment completion, or closure information as if they already existed at registration.

1. Recommended Portal Workflow

MoU / Consultancy Agreement signed

Department submits Online Consultancy Registration

System validates required fields and generates Consultancy ID

Consultancy is undertaken; progress, deliverables and supporting documents are maintained in the portal

Department submits Closure Form after completion

System generates the final Consultancy Closure Record

2. Document Outputs

| Output | When generated | Contents |
| --- | --- | --- |
| Consultancy Registration Record | After registration approval | Department, client, consultancy, agreement and initial financial/document details |
| Consultancy Monitoring Record | During the consultancy | Team, milestones, updates, resources, documents, payments and compliance |
| Consultancy Closure Record | After closure approval | Completion, outcomes, final deliverables, acceptance, final payment and closure confirmation |

3. Important Data-Control Changes

Do not pre-populate future progress or closure information in the registration record.

Use controlled status values such as Draft, Submitted, Under Review, Approved, Active, On Hold, Completed and Closed.

Use system-generated Consultancy ID, registration timestamp, document references and audit timestamps wherever possible.

Financial fields should distinguish Total Value, Amount Received, Balance Pending and Payment Status.

Supporting documents should be linked by portal reference; they should not be embedded in the generated record.

Closure fields should remain unavailable until the consultancy is eligible for closure.

PAGE 1 — CONSULTANCY REGISTRATION RECORD

| Field | Sample / System Value |
| --- | --- |
| Consultancy ID | CAIAS/CON/2026-27/001 |
| Registration Date | 08 September 2026 |
| Academic Year | 2026–27 |
| Status | ACTIVE |

1. Department Details

| Field | Sample Data |
| --- | --- |
| Department | School of Computer Science |
| HOD | Dr. Priya Nair |
| Department Consultancy Coordinator | Dr. Arun Kumar |
| Email | arun.kumar@caias.example |
| Contact | +91 90000 00001 |

2. Client / Organisation Details

| Field | Sample Data |
| --- | --- |
| Organisation | ABC Technologies Pvt. Ltd. |
| Organisation Type | Private Company |
| Address | 12 Innovation Park, Whitefield, Bengaluru – 560066 |
| Contact Person | Ms. Meera Shah |
| Designation | Head – Business Analytics |
| Email | meera.shah@abctech.example |
| Contact | +91 90000 00002 |

3. Consultancy Details

Title: AI-Based Business Analytics Training and Advisory

Category: AI / Data / Technology Consultancy

Start Date: 10 September 2026

Expected Completion: 30 November 2026

Scope: Design and deliver an applied business analytics programme covering data preparation, dashboard development, AI-assisted analysis and interpretation of business datasets.

Objectives: Build practical analytics capability among the client team and provide an implementation-oriented advisory framework.

Expected Outcomes: Training completion, analytics dashboard prototype, technical guidance note and final consultancy report.

4. Agreement Details

| Field | Sample Data |
| --- | --- |
| Agreement Type | Consultancy Agreement |
| Agreement Reference | ABC/CAIAS/2026/12 |
| Agreement Date | 08 September 2026 |
| Signed Agreement | Available in Portal |
| NDA / Confidentiality | Available in Portal |

PAGE 2 — CONSULTANCY MONITORING RECORD

5. Consultancy Team

| Name | Role | Department | Responsibility |
| --- | --- | --- | --- |
| Dr. Arun Kumar | Principal Consultant | Computer Science | Project supervision & client coordination |
| Dr. Neha Rao | Co-Consultant | Computer Science | Analytics & dashboard development |
| Mr. Rohan Mathew | Technical Expert | Computer Science | AI tools & technical support |

6. Deliverables & Milestones

| Deliverable | Target Date | Status |
| --- | --- | --- |
| Requirement Analysis | 20 Sep 2026 | Completed |
| Analytics Training Programme | 31 Oct 2026 | In Progress |
| Dashboard Prototype | 15 Nov 2026 | In Progress |
| Final Consultancy Report | 30 Nov 2026 | Pending |

7. Financial Details

| Field | Sample Data |
| --- | --- |
| Total Consultancy Value | ₹2,50,000 |
| Payment Structure | Advance + Balance |
| Advance | ₹1,00,000 |
| Balance | ₹1,50,000 |
| Payment Status | Partially Received |
| Payment Account | CAIAS designated institutional account |

8. CAIAS Resources Used

Institutional Resources: Yes

Resources: Computer systems, AI/data analytics software, training facilities and meeting space.

9. Intellectual Property & Confidentiality

| Field | Status |
| --- | --- |
| Confidential Information | Yes |
| NDA | Executed |
| Intellectual Property | As specified in Consultancy Agreement |
| Client Data | Used for consultancy |

10. Document Record

| Document | Status | Portal Reference |
| --- | --- | --- |
| Signed Consultancy Agreement | Available | DOC/CON/001/01 |
| NDA | Available | DOC/CON/001/02 |
| Project Proposal | Available | DOC/CON/001/03 |

Note: Actual uploaded documents should remain in the portal repository. The generated PDF/Word record should show only their availability and reference number.

11. Progress / Update History

| Date | Activity / Update | Deliverable | Status |
| --- | --- | --- | --- |
| 15 Sep 2026 | Client requirement discussion completed | Requirement Analysis | Completed |
| 28 Sep 2026 | Training module submitted | Training Programme | In Progress |
| 12 Oct 2026 | First training session completed | Training Programme | In Progress |
| 01 Nov 2026 | Dashboard prototype initiated | Dashboard | In Progress |

PAGE 3 — CONSULTANCY CLOSURE RECORD

12. Payment Summary

| Field | Sample Data |
| --- | --- |
| Total Consultancy Value | ₹2,50,000 |
| Amount Received | ₹1,00,000 |
| Balance Pending | ₹1,50,000 |
| Payment Status | Partially Received |

13. Closure / Exit Record

| Field | Sample Data |
| --- | --- |
| Actual Completion Date | 30 November 2026 |
| Work Completed | All agreed consultancy activities completed |
| Major Outcomes | Training completed, dashboard prototype delivered and implementation guidance provided |
| Final Deliverables | Submitted |
| Client Acceptance | Yes |
| Final Payment | Fully Received |
| Final Status | COMPLETED & CLOSED |

14. Closure Documents

| Document | Status | Reference |
| --- | --- | --- |
| Final Consultancy Report | Available | DOC/CON/001/10 |
| Client Completion Confirmation | Available | DOC/CON/001/11 |
| Final Invoice / Payment Record | Available | DOC/CON/001/12 |

15. Declaration & System Record

Declaration: I confirm that the information recorded in this consultancy record is accurate and that the consultancy has been undertaken in accordance with the CAIAS Consultancy Services – Framework & Guidelines and applicable institutional policies.

| Field | System Record |
| --- | --- |
| Department Confirmation | Electronically Confirmed |
| Submitted By | Department Consultancy Coordinator |
| Submission Date | 08 September 2026 |
| Closure Submitted By | Department Consultancy Coordinator |
| Closure Date | 30 November 2026 |
| IIIC / Institutional Record Status | COMPLETED & CLOSED |

16. Recommended Portal Validation Rules

Registration cannot be submitted without required department, client, consultancy and agreement fields.

Expected Completion Date must not precede Start Date.

Actual Completion Date is entered only at closure.

Final Payment should be marked Fully Received only when the portal/payment record confirms full settlement.

Client Acceptance should be captured as a closure-stage field.

Closure cannot be finalized while mandatory final deliverables or completion confirmation are missing.

Every change to status, payment, deliverable and closure information should retain an audit timestamp and user identity.

System-generated records should display version/date information so later corrections are traceable.